## Methodology - editable
These tables are editable - you should review them to ensure they meet your project requirements |  | LOW RISK | MEDIUM RISK | HIGH RISK
Settings | Weighting | 1 | 3 | 5 |  |  |  | < Raw score*
|  | 50% | 75% | 100% |  |  |  | < Upper limit*
Cost | 1 | < 5% of program budget | Between 5-15% of program budget | > 15% of program budget | 1 | 3 | 5
| 1 | ±10% confidence in estimate | ±25% confidence in estimate | > 25% margin of error assumed in estimate | 1 | 3 | 5
| 1 | Costs are fully budgeted or covered by external client | Costs are partially allowed for in the annual budget or financed by the client | Expected costs are neither allowed for in the annual budget nor externally financed | 1 | 3 | 5
Time | 1 | > 3 months | > 6 months | > 6 months to deliver | 1 | 3 | 5
| 1 | ± 10% confidence in estimate | ± 25% confidence in estimate | > 25% margin of error assumed in estimate | 1 | 3 | 5
| 1 | No fixed deadline for delivery | A preferred (but not mandated) delivery window | Must be delivered on or by a fixed date | 1 | 3 | 5
Scope | 1 | We've delivered five (5) or more times | We've delivered at least once before | We have never successfully delivered a project like this | 1 | 3 | 5
Impact | 1 | Will noticeably impact one (1) department in our organization | Will noticeably impact several departments in our organization | Will noticeably impact most or all of our organization | 1 | 3 | 5
| 1 | No major subsequent dependencies | Some major subsequent dependencies | Several major subsequent dependencies | 1 | 3 | 5
| 1 | No employee or public health and/or safety risks | Employees and/or the public may be at risk of minor injury or illness during project delivery | Employees and/or the public may be at risk of serious injury, illness or loss of life during project delivery | 1 | 3 | 5
| 1 | Outcomes will fulfil one (1) strategic objective of our organization | Outcomes will fulfil several strategic objectives of our organization | Outcomes will fulfil most or all of the strategic objectives of our organization | 1 | 3 | 5
Stakeholders | 1 | Can be fully delivered by our current staff | Work will need to be shared with proven, existing partners | Will depend on collaboration with new and/or unknown partners | 1 | 3 | 5
| 1 | Only of internal interest to our organization | Sly to be some community interest in the project and/or its outcomes | Will be highly visible in the community | 1 | 3 | 5
Definitions | [6 empty] | 65
Raw score | The weighting assigned to a risk. If you want high risks to be more extremely weighted, assign a proportionately higher score to the high risk category.
Upper limit | The point at which a risk converts from low to medium and medium to high. A high score for low and medium means the organisation has a high tolerance for (or willingness to take on) risk. The high risk score is locked at 100%.

## Calculator
PROJECT PROFILE TOOL
Project name: |  |  | Notes
Use the dropdown menus to select the relevant risks
Cost | > 15% of program budget | 5
| > 25% margin of error assumed in estimate | 5
| Expected costs are neither allowed for in the annual budget nor externally financed | 5
Time | > 6 months to deliver | 5
| > 25% margin of error assumed in estimate | 5
| Must be delivered on or by a fixed date | 5
Scope | We have never successfully delivered a project like this | 5
Impact | Will noticeably impact most or all of our organization | 5
| Several major subsequent dependencies | 5
| Employees and/or the public may be at risk of serious injury, illness or loss of life during project delivery | 5
| Outcomes will fulfil most or all of the strategic objectives of our organization | 5
Stakeholders | Will depend on collaboration with new and/or unknown partners | 5
| Will be highly visible in the community | 5
THIS PROJECT IS: | HIGH RISK | 1